## Daily Routine
SUPERINTENDENT DAILY FIELD MANAGEMENT ROUTINE
Sedalia – Fire Station ¦ Bowling Alley ¦ Fire Training
Purpose: Maintain intentional field presence while protecting time for interior coordination, documentation, quality control, and planning.
FIELD OPERATING RULE: A subcontractor question, coordination issue, schedule concern, material question, or normal field problem is NOT an emergency. Questions will be documented, prioritized, and answered through the scheduled walk / coordination process. Immediate interruption is reserved for a true emergency such as an accident or injury, an active safety hazard requiring immediate action, OSHA or another regulatory authority arriving on site, a utility strike or property-damage event, or another condition where waiting creates an immediate safety or significant project risk.
Time | Activity | Focus / Purpose | Description | Interruption Guideline | Notes
7:00–7:15 AM | Daily Startup / Planning | Set priorities before the first walk | • Review work, inspections & deliveries • Identify critical issues / constraints • Prepare for field walk | Emergency / critical only
7:15–7:45 AM | Morning Field Walk – Fire Station & Bowling Alley | Foreman check-in + identify issues | • Walk Fire Station + Bowling; check foremen/manpower • Document issue, needed-by time & photo • Save routine problem-solving for huddle | Open discussion with foremen; document rather than immediately chase non-critical issues
7:45–8:00 AM | Organize Morning Walk Notes | Turn field observations into an action list | • Organize issues by building / priority • Match notes with photos • Prepare huddle list | Critical / work-stopping issues only
8:00–8:20 AM | Team Coordination Huddle – Frank / Tim / Caleb | Prioritize field issues + assign communication / follow-up | • Review issues / photos as a team • Assign owner, priority & needed-by date • Assign follow-up / Action Tracker | No interruptions except a true emergency
8:20–10:15 AM | Protected Management / Problem-Solving Time | Resolve issues + interior management | • Resolve priority action items • Coordinate drawings, RFIs, subs & finishes • Update QC / documentation | Critical / work-stopping issues only
10:15–11:00 AM | Pre-Lunch Field Walk – All Active Areas | Follow-up + Fire Training check | • Follow up Fire Station + Bowling • Verify progress / quality • Walk Fire Training; document issues | Normal field questions handled here
11:00 AM–12:00 PM | Interior Coordination / Follow-Up | Finish sequencing + new field issues | • Resolve pre-lunch issues • Coordinate interior finish constraints • Confirm next-trade readiness | Critical issues only
11:30 AM–12:30 PM | Lunch | Break / recharge | • Take approximately 1 hour for lunch • Adjust slightly as field conditions require | True emergency only
12:30–1:30 PM | Documentation + Look-Ahead Planning | Record progress + prepare upcoming work | • Update report, photos, QC & tracker • Review look-ahead / manpower / inspections • Follow up open items | Critical issues only
1:30–2:15 PM | Afternoon Field Walk | QC + production + issue follow-up | • Verify progress vs. commitments • Check quality / corrections; take photos • Document new issues | Open discussion with foremen
2:15–3:15 PM | Protected Management / Next-Day Preparation | Close issues + prepare tomorrow | • Resolve afternoon items / deficiencies • Confirm tomorrow’s crews, materials & inspections • Escalate production impacts | Critical issues only
3:15–3:45 PM | End-of-Shift Field Loop | Completion + readiness verification | • Verify work / housekeeping • Check staging & tomorrow readiness • Capture final photos | Brief closeout questions
3:45–4:30 PM

## Daily Action Tracker
SEDALIA – DAILY COORDINATION LOG & ACTION TRACKER
Use during the Frank / Tim / Caleb morning huddle. Document field issues with a photo when applicable, assign an owner, establish priority and needed-by date, and track each item through resolution.
TRACKER SUMMARY | COUNT |  | PRIORITY GUIDE HIGH – Needs action today or could affect near-term production, inspection, manpower, procurement, or schedule. MEDIUM – Important follow-up, but work can continue while it is being resolved. LOW – Routine coordination, future planning, documentation, or an item that can reasonably wait.
Open / In Progress | 10
High Priority Open | 1
Waiting | 0
Date | Building / Area | Issue / Task | Photo Ref. | Priority | Responsible | Action / Follow-Up Required | Needed By | Status | Follow-Up / Resolution | Last Follow-Up
2026-08-16 | Bowling Alley | Projector Wall Finish |  | Medium | Tim | Review on plans and discuss level of finish required. |  | Complete | Level 4 Finish, projectors are fixed and framed | 2026-08-17
2026-08-16 | Bowling Alley | Altro Whiterock Wall Protection |  | Medium | Frank | Need to order. Looking at 4 products that are in specifications and ridiculously expensive. |  | Open
2026-08-16 | Site / Utilities | Pricing from Elite Fence for fencing |  | Medium | Caleb | Follow up and find out if they will honor their price and need to get contract. |  | Open
2026-08-16 | Bowling Alley | Flagpole base |  | Medium | Caleb | Reinhardt and finding out how they prefer to pour before. Bass to be on site 08/31 |  | Open
2026-08-16 | Bowling Alley | Pricing for PR-1 (Electrical Site Light Pole Receptacle Addition) |  | Medium | Frank | Review of pricing and change events to send to owner for added outlets on bldg and light poles. |  | Complete | PR-01 Light Pole Receptacle add created CE#042 Sent 08/17 | 2026-08-17
2026-08-17 | Bowling Alley | Pricing for PR-1 (E-401 Added receptacles per recommendation of health department & DBL oven Revision) |  | Medium | Frank |  |  | Complete | PR-01 Revisions created CE#043 Sent 08/17 | 2026-08-17
2026-08-17 | Bowling Alley | Pricing for PR-1 E-101 |  | Medium | Frank |  |  | Complete | PR-01 Revisions created CE#044 Sent 08/17 | 2026-08-17
2026-08-16 | General | Get contract for final clean out |  | Medium | Frank |  |  | Open
2026-08-16 | Bowling Alley | Access Controls |  | Medium | Frank | Spoke with Amy and they still want access controls from nightwatch. She was calling Doug. |  | Open |  | 2026-08-14
2026-08-16 | Bowling Alley | Landscaping |  | Medium | Caleb | Get pricing for options discussed during meeting |  | Open
2026-08-16 | Site / Utilities | Ashphalt Revised Pricing |  | Medium | Caleb | Need to finalize Capital pricing with revisions to paving requested. |  | Open | Should have revised pricing 8/17 from Quintin
2026-08-16 | General | CO to Bass Concrete for HD concrete revisions. |  | Medium | Frank | Send CO for revisions |  | Complete | Need deduct for base being placed by Do-Rite for curb & gutter | 2026-08-16
2026-08-16 | General | Need deduct for base being placed by Do-Rite for curb & gutter |  | Medium | Frank |  |  | Open | Sent to Bass & Do-Rite | 2026-08-16
2026-08-16 | Bowling Alley | Review details for AV keypad |  | Medium | Frank |  |  | Open | Sent to email to Parks for availability | 2026-08-16
2026-08-16 | General | Review pay application for July |  | High | Caleb | Frank/Caleb |  | Open | Need to get submitted